## RACI Matrix
RACI MATRIX — CloudSuite Tiered Pricing Rollout
Task | Product | Engineering | Finance | Support | Sales | BA (self)
Define pricing tiers & limits | A | I | C | C | C | R
Write BRD & user stories | C | C | I | I | I | R/A
Build proration & billing logic | I | R/A | C | I | I | C
Update self-serve checkout UI | A | R | I | I | I | C
Multi-currency QA (EUR/GBP/USD) | I | R | A | I | I | C
Update Terms of Service / legal review | A | I | C | I | I | R
Migrate existing customers to new tiers | A | R | C | C | C | C
Update Support macros & training | I | I | I | R/A | I | C
Customer launch communications | A | I | I | C | R | C
Post-launch monitoring & reconciliation | C | C | R/A | C | I | R
Legend: R = Responsible · A = Accountable · C = Consulted · I = Informed

## Risk Log
RISK LOG — CloudSuite Tiered Pricing Rollout
# | Risk | Likelihood | Impact | Mitigation | Owner | Status
1 | Proration edge cases (e.g. downgrade below current usage, same-day upgrade+downgrade) produce incorrect charges. | Medium | High | Define explicit rules for every edge case in user stories (US-02, US-03); Engineering to unit-test each case before launch. | Engineering | Open
2 | Currency conversion rate used for a transaction differs from the rate shown in the customer's preview, causing a billing dispute. | Low | High | Lock and store the exact rate at preview time, not just at confirmation (see US-07); reuse locked rate if confirmed within a defined time window. | Engineering | Open
3 | Existing annual customers see the migration as a disguised price increase and churn at renewal. | Medium | High | 30-day advance notice email (US-06); consider a time-boxed grandfathered-price option — flagged to Product as a decision, not assumed. | Product / Sales | Open
4 | Support team isn't ready to answer billing questions on the new tiers at launch, causing a ticket spike. | Medium | Medium | Update Support macros and run a training session 1 week before launch; provide Support with a FAQ covering every user story's edge cases. | Support | Open
5 | Finance's revenue recognition system can't ingest the new automated billing feed in time for launch. | Low | High | Confirm Finance systems' API/feed compatibility in technical discovery (Section 8 of BRD) before committing to a launch date. | Finance | Open
6 | A failed or declined payment during a mid-cycle upgrade leaves a customer with new-tier access but no successful charge. | Medium | Medium | Gate access unlock on payment confirmation, not on confirmation click; add automatic retry + grace-period logic with clear customer messaging. | Engineering | Open
7 | VAT/tax recalculation for EU customers on prorated amounts is handled inconsistently across tiers. | Low | Medium | Route tax calculation through the existing tax engine for every proration event, not just full-cycle invoices; explicit QA case. | Engineering / Finance | Open